## Backend
Bi-WEEKLY SPRINT 1: 23rd March - 3rd April
Backend
WEEK 1: 23 - 28 March
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Backend Architecture & Project Setup | Define the backend architecture, create the project folder structure, set up the FastAPI application, establish main API routes and share the API contract with all teams. | Working FastAPI base project with organised folder structure, main.py, basic routes (/ and /health), and BACKEND_PLAN.txt shared with team
Lucas | API Routes Implementation | Create the backend route files for player, crowd, and test functionality and implement the initial API endpoints required for frontend and integration testing. | Route files created (players, crowd, test) with working endpoints /api/test, /api/players, and /api/crowd
William | Mock Service Layer — Setup | Create player_client.py and crowd_client.py returning mock JSON responses. Add USE_MOCK_SERVICES flag to .env so mocks can be toggled on/off without code changes. | player_client.py and crowd_client.py created with structured mock JSON responses and USE_MOCK_SERVICES flag supported
Prabhnoor | Configuration Setup | Implement config.py to load all environment variables from .env using python-dotenv. Fill in .env with local dev values including USE_MOCK_SERVICES=true as default. | .env and config.py completed with all required environment variables including mock service toggle
WEEK 2: 29 March - 3 April
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | CORS + Route Wiring + Frontend Checkpoint 1 + Contract Push | Configure CORS in main.py to allow frontend on localhost:3000. Wire all completed routes. Share BACKEND_PLAN.txt and Swagger URL with frontend team. Send contract template to player and crowd teams. Review and merge all week 1 PRs. | CORS configured, all routes wired, API contract shared with frontend team, contract confirmation requested from player and crowd teams
Lucas | Auth Schemas | Implement schemas/auth.py (RegisterRequest, LoginRequest, AuthResponse, UserResponse) and schemas/health.py (HealthResponse). | Pydantic schemas ready for use in auth routes
William | Mock Services Connected to Routes | Connect player_client.py and crowd_client.py to the API routes. Verify mock responses return correctly through the gateway when USE_MOCK_SERVICES=true. | Mock services integrated and returning structured data through the routes
Prabhnoor | Database Setup | Implement database.py (PostgreSQL async connection via SQLAlchemy) and models.py (users and jobs table definitions). Set up local PostgreSQL and confirm connection works. | Working database connection with users and jobs tables created
Bi-WEEKLY SPRINT 2: 4th - 17th April
Backend
WEEK 3: 4 - 10 April
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Auth Core Implementation + Contract Follow-up | Implement auth/hashing.py (bcrypt) and auth/jwt.py (JWT tokens). Implement RBAC dependencies get_current_user and require_admin. Chase up player and crowd teams for contract confirmation. Review all PRs. | Working auth system with password hashing, JWT tokens, and role-based access control. Contract status known.
Lucas | Auth Routes | Implement routes/auth.py with POST /auth/register, POST /auth/login, and GET /auth/me endpoints. | Auth endpoints working and returning correct responses
William | Job Schemas | Implement schemas/jobs.py with JobSummary, JobDetail, JobListResponse, and UploadResponse Pydantic models. | Job schemas ready for use in upload and job routes
Prabhnoor | Global Error Handler & Logging Middleware | Add global exception handler to main.py to catch all unhandled errors and return clean JSON. Add request logging middleware. | All unhandled errors return clean JSON responses, all requests logged
WEEK 4: 11 - 17 April
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Video Upload Route + Frontend Checkpoint 2 | Implement routes/upload.py to validate video format, save to uploads/, create a job in the database, and return job_id immediately. Wire route into main.py. Verify frontend can connect to /health and /auth/login. | POST /upload working, job created in DB, frontend connection verified
Lucas | Job Routes | Implement routes/jobs.py with GET /status/{job_id}, GET /jobs, GET /jobs/{job_id}, POST /jobs/{job_id}/retry, and DELETE /jobs/{job_id} with RBAC enforced. | All job endpoints working with correct role-based access control
William | Background Task — process_video() | Implement process_video() background task using asyncio.gather. Respect USE_MOCK_SERVICES flag. Handle partial results if one service fails. Update job status in DB to done, partial, or failed. | Background processing working with mock toggle support, job status updated correctly
Prabhnoor | Auth & Health Tests | Write tests/test_auth.py (register, login, token validation) and tests/test_health.py. | Auth and health tests passing
Bi-WEEKLY SPRINT 3: 17th April - 1st May
Backend
WEEK 5: 17 - 24 April
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Finalise API Contracts + Integration Decision | Finalise confirmed contracts with player and crowd teams. Update BACKEND_PLAN.txt and .env with real service URLs. Decide whether to proceed with real integration or stay on mocks based on other teams' readiness. Review all PRs. | Contracts finalised, integration decision made, .env updated accordingly
Lucas | Upload & Job Tests | Write tests/test_upload.py (file format validation, job creation) and tests/test_jobs.py (job status, pagination, retry) using mocked service responses. | Upload and job tests passing with mocked services
William | Real Player Service Integration (if contracts confirmed) | If player team contract is confirmed, update player_client.py to call real player service. Keep USE_MOCK_SERVICES flag — real client used only when flag is false. If not confirmed, keep mock and document blockers. | player_client.py supports both mock and real mode via USE_MOCK_SERVICES flag
Prabhnoor | Real Crowd Service Integration (if contracts confirmed) | If crowd team contract is confirmed, update crowd_client.py to call real crowd service. Keep USE_MOCK_SERVICES flag. If not confirmed, keep mock and document blockers. | crowd_client.py supports both mock and real mode via USE_MOCK_SERVICES flag
WEEK 6: 25 April - 1 May
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Core Frontend Integration Checkpoint 3 + Demo Mode Prep | Run full pipeline locally with both real and mock modes. Verify frontend can hit /upload and /status/{job_id} end-to-end. Confirm demo can run in Mode A (real services) or Mode B (mock fallback). Review and merge all integration PRs. | Both demo modes verified — Mode A with real services and Mode B with mock fallback
Lucas | Route Error Handling | Handle timeout errors from player and crowd services, return 400 for bad video formats, and return partial or failed status when a service is down. | All error cases handled with correct HTTP status codes and clean responses
William | Retry Endpoint Testing | Test POST /jobs/{job_id}/retry with a real partial failure scenario. Verify asyncio.gather handles one service failing correctly and only the failed service is retried. | Retry working correctly in real partial failure scenarios
Prabhnoor | Integration Test Suite | Run all tests against real services if available. If not, run against mocks. Fix any failures and document integration status clearly. | All tests passing, integration status documented
Bi-WEEKLY SPRINT 4: 1st - 15th May
Backend
WEEK 7: 1 - 8 May — BUFFER / CATCH-UP WEEK
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | Buffer — Fix Integration Issues or Start Docker | If real service integration is behind, use this week to resolve blockers and stabilise integration. If integration is on track, begin Dockerfile and docker-compose.yml setup. Review all PRs. | Integration stable or Docker setup started depending on progress
Lucas | Buffer — Fix Failing Tests or Docker Config | Fix any remaining test failures or integration issues. If on track, swap .env URLs from localhost to Docker service names and begin Docker testing. | Tests passing or Docker config started
William | Buffer — Service Client Fixes or Docker Testing | Resolve any service client issues from integration. If on track, test player_client.py and crowd_client.py with Docker service names. | Service clients stable or Docker-ready
Prabhnoor | Buffer — Test Suite Fixes or Docker Test Run | Fix any outstanding test failures. If on track, run the full test suite inside Docker and fix any Docker-specific issues. | Test suite stable or passing inside Docker
WEEK 8: 8 - 15 May
MEMBER | TASK | DESCRIPTION | OUTPUT
Tomin | README + Final Demo Checkpoint 4 | Write README.md with local and Docker setup instructions. Do final review of all code. Run full end-to-end demo — attempt Mode A (real services) first, fall back to Mode B (mock) if needed. Coordinate final demo run with all teams. | Complete README, all code reviewed, demo confirmed working in at least one mode
Lucas | Swagger Docs Polish | Verify /docs looks clean and accurate. Add any missing response descriptions to all endpoints. | Clean and accurate Swagger UI at /docs
William | Logging & Cleanup | Add request and response logging to all service clients. Clean up any leftover debug code. | All service client calls logged, codebase clean
Prabhnoor | Final Test Run & Cleanup | Run the complete test suite one final time. Ensure all tests pass. Remove any leftover debug code. | All tests green, codebase clean and demo-ready